## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US-001 | Collect user and product data from e-commerce dataset | Must Have |  | Himanshu Sharma | Completed
1 | 1 | US-002 | Handle data inconsistencies and clean datasets | Must Have | US-001 | Himanshu Sharma | Completed
1 | 1 | US-003 | Build user-item interaction matrix for recommendations | Must Have | US-002 | Himanshu Sharma | Completed
2 | 2 | US-004 | Select and implement recommendation algorithm (Collaborative Filtering) | Must Have | US-003 | Himanshu Sharma | Completed
2 | 2 | US-005 | Train model on prepared data from Milestone 1 | Must Have | US-004 | Himanshu Sharma | Completed
2 | 2 | US-006 | Perform initial model tuning and parameter optimization | Should Have | US-005 | Himanshu Sharma | Completed
3 | 3 | US-007 | Calculate precision, recall, and F1-score metrics | Must Have | US-005 | Himanshu Sharma | Completed
3 | 3 | US-008 | Analyze model performance across different scenarios | Must Have | US-007 | Himanshu Sharma | Completed
3 | 3 | US-009 | Fine-tune model based on evaluation results | Should Have | US-008 | Himanshu Sharma | Completed
3 | 3 | US-010 | Test different recommendation scenarios and validate accuracy | Must Have | US-009 | Himanshu Sharma | Completed
4 | 4 | US-011 | Implement frontend with input form for user preferences | Must Have | US-010 | Himanshu Sharma | In Progress
4 | 4 | US-012 | Connect backend prediction engine to frontend | Must Have | US-011 | Himanshu Sharma | Planned
4 | 4 | US-013 | Deploy application on preferred platform (Heroku/AWS) | Must Have | US-012 | Himanshu Sharma | Planned
4 | 4 | US-014 | Perform final testing with multiple sample cases | Should Have | US-013 | Himanshu Sharma | Planned
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
SPRINT 1 BACKLOG
US-001 | T-001 | Download e-commerce dataset from Kaggle | 2025-01-08 | 2025-01-08 | Himanshu Sharma | Data Collection | Completed | 2
US-002 | T-002 | Explore dataset structure and identify missing values | 2025-01-09 | 2025-01-09 | Himanshu Sharma | Data Analysis | Completed | 3
US-002 | T-003 | Clean interaction data (events.csv) | 2025-01-10 | 2025-01-11 | Himanshu Sharma | Data Cleaning | Completed | 6
US-002 | T-004 | Clean product/item data | 2025-01-12 | 2025-01-13 | Himanshu Sharma | Data Cleaning | Completed | 5
US-003 | T-005 | Build user-item interaction matrix | 2025-01-14 | 2025-01-15 | Himanshu Sharma | Feature Engineering | Completed | 8
SPRINT 2 BACKLOG | T-006 | Save cleaned datasets for model development | 2025-01-15 | 2025-01-15 | Himanshu Sharma | Data Export | Completed | 2
US-004 | T-008 | Implement user-based collaborative filtering | 2025-01-17 | 2025-01-19 | Himanshu Sharma | Development | Completed | 10
US-005 | T-009 | Split data into train and test sets | 2025-01-20 | 2025-01-20 | Himanshu Sharma | Data Preparation | Completed | 3
US-005 | T-010 | Train recommendation model on prepared data | 2025-01-21 | 2025-01-22 | Himanshu Sharma | Model Training | Completed | 8
SPRINT 3 BACKLOG | T-011 | Tune hyperparameters (k neighbors, similarity metric) | 2025-01-23 | 2025-01-24 | Himanshu Sharma | Optimization | Completed | 6
US-008 | T-013 | Analyze performance across k values (5, 10, 15) | 2025-01-26 | 2025-01-27 | Himanshu Sharma | Analysis | Completed | 6
US-008 | T-014 | Document model performance metrics | 2025-01-27 | 2025-01-27 | Himanshu Sharma | Documentation | Completed | 3
US-009 | T-015 | Fine-tune model based on evaluation results | 2025-01-28 | 2025-01-28 | Himanshu Sharma | Optimization | Completed | 4
SPRINT 4 BACKLOG | T-016 | Test different recommendation scenarios | 2025-01-28 | 2025-01-28 | Himanshu Sharma | Testing | Completed | 4
US-011 | T-018 | Implement HTML/CSS frontend with input form | 2025-02-05 | 2025-02-07 | Himanshu Sharma | Development | Planned | 10
US-012 | T-019 | Create Flask/FastAPI backend API | 2025-02-07 | 2025-02-08 | Himanshu Sharma | Development | Planned | 8
US-012 | T-020 | Integrate prediction engine with API | 2025-02-08 | 2025-02-09 | Himanshu Sharma | Integration | Planned | 6
US-013 | T-021 | Deploy application to cloud platform | 2025-02-09 | 2025-02-09 | Himanshu Sharma | Deployment | Planned | 4
US-014 | T-022 | Perform end-to-end testing with sample cases | 2025-02-10 | 2025-02-10 | Himanshu Sharma | Testing | Planned | 3
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | 1 | None | Dataset successfully downloaded from Kaggle
1 | 3 | Missing values in product properties | Implemented data cleaning strategy
2 | 2 | Similarity computation taking long time | Optimized using sparse matrices
2 | 4 | None | Successfully trained collaborative filtering model
3 | 2 | Low recall for k=5 | Tested multiple k values (5, 10, 15)
3 | 4 | None | Achieved best performance with k=10 (F1=0.38)
4 | 1 | Need to decide on deployment platform | Researching Heroku vs AWS options

## Retrospection
Sprint | What Went Well | What Could Be Improved | Action Items | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
Sprint 1 | Successfully prepared clean datasets and built interaction matrix | Data cleaning took longer than expected due to missing values | Allocate more time for data exploration in future sprints
Sprint 2 | Implemented collaborative filtering algorithm successfully | Initial training was slow - needed optimization | Research optimization techniques before implementation
Sprint 3 | Achieved good model performance metrics (Precision: 0.326, Recall: 0.459, F1: 0.380 @ k=10) | Testing different scenarios could have been more comprehensive | Create detailed test cases before evaluation phase
Sprint 4 | Frontend design in progress | Still deciding on deployment platform | Make deployment decisions earlier in the sprint
5
6
7