## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Himanshu Sharma | 2025-01-11 | Missing values in item properties causing errors | Sprint 1 | Himanshu Sharma | Data Quality | Implemented fillna() for missing values | 2025-01-11 | Closed | Fixed during data cleaning
2 | Himanshu Sharma | 2025-01-14 | User-item matrix dimensions mismatch | Sprint 1 | Himanshu Sharma | Logic Error | Corrected matrix construction logic | 2025-01-14 | Closed | Verified matrix shape
3 | Himanshu Sharma | 2025-01-19 | Similarity computation memory overflow for large datasets | Sprint 2 | Himanshu Sharma | Performance | Used sparse matrix representation | 2025-01-20 | Closed | Reduced memory usage by 70%
4 | Himanshu Sharma | 2025-01-21 | Model predictions returning NaN values | Sprint 2 | Himanshu Sharma | Logic Error | Added handling for cold start users | 2025-01-22 | Closed | Implemented default recommendations
5 | Himanshu Sharma | 2025-01-26 | Low precision score (0.27) for k=5 neighbors | Sprint 3 | Himanshu Sharma | Model Performance | Tuned k parameter to 10 | 2025-01-27 | Closed | Improved precision to 0.326
6 | Himanshu Sharma | 2025-01-27 | F1-score calculation giving incorrect values | Sprint 3 | Himanshu Sharma | Calculation Error | Fixed formula: 2*P*R/(P+R) | 2025-01-27 | Closed | Verified with manual calculation
7 | Himanshu Sharma | 2025-02-04 | Frontend form validation not working | Sprint 4 | Himanshu Sharma | UI Bug | Add JavaScript validation |  | Open | In progress

## Sheet2
Logical
User Interface
Maintainability
Standards
Others